NAME:

Zain Zaheer (53812)

Ahmad Raza (53302)

Atia Rahat (57325)

PROGRAM:

BSSE-6

COURSE:

SPM

PROJECT:

Sales Point

DOCUMENT:

LAB 3

(Project Initiation and Planning)

SUBMITTED TO:

Sir Waqar Mehmood

- Project Description:

- Project Title: SalesPoint (Sales and Inventory Management System)

- Brief System Overview: An MIS designed for small/medium retail stores to automate sales processing and inventory management, replacing manual record-keeping.

- Problem Statement: Manual systems are inefficient, prone to errors in billing/stock counting, and risk data loss.

- Project Objectives:

  - Automate retail operations and reduce human error.

  - Provide real-time inventory updates and automated invoicing.

  - Generate sales reports for business analysis.

- Stakeholders: Store Owner (Client), Admin and Sales Staff (Users), and Developers (Project Team)

- Feasibility Analysis:

- Technical Feasibility: The team will use standard web or desktop technologies (e.g., C#/.NET or Java with SQL database).

- Economic Feasibility: High ROI expected through reduced labor time and prevention of stock shortages/overstocking.

- Operational Feasibility: High user acceptance as it simplifies daily tasks for sales staff and provides owners with clear control.

3. Resource Planning:

| Resource Type | Description | Allocation |
| --- | --- | --- |
| Human | Team Leader, Technical Analyst, Document Coordinator | Full-time for project duration |
| Hardware | Development PCs, Receipt Printer (for testing) | 1 per developer |
| Software | MS Project, SQL Server, IDE (VS Code/Visual Studio) | Standard Licenses |

4. Time Planning (Project Schedule):

- Phase 1: Requirements (Week 1): Finalize stakeholder needs and system specs.

- Phase 2: Design (Week 2): Database schema and UI wireframes.

- Phase 3: Development (Week 3-5): Coding the Sales and Inventory modules.

- Phase 4: Testing & Rollout (Week 6): Bug fixing and deployment.

# 5. Cost Planning:

| ### Cost Category | ### Details | ### Amount (PKR) |
| --- | --- | --- |
| ### Human Resources | ### Salaries (Ahmad – Team Lead, Atia – Analyst & Documentation, Zain – Developer/Tester) | ### 300,000 |
| ### Hardware & Infrastructure | ### Laptops + Cloud Hosting | ### 120,000 |
| ### Tools & Software | ### Licenses / API Keys | ### 20,000 |
| ### Testing & Contingency | ### QA tools + Buffer | ### 50,000 |
| ### Training & Rollout | ### User training materials | ### 30,000 |
| ### Total Project Budget |  | ### 520,000 |

### Basic Cost-Benefit Analysis:

- Total Cost = PKR 520,000

- Expected First-Year Benefit = PKR 2,300,000

- Net Benefit = PKR 1,780,000 (Positive ROI)

# 6. Team Planning:

### Roles and Responsibilities:

- Project Manager / Team Leader: Ahmad Raza
Project coordination, client communication, schedule & budget control

- Technical Analyst & Documentation Lead: Atia Rahat
Requirements analysis, system design support, documentation

- Developer & Tester: Zain
Frontend, backend development, testing & integration

# 7. Risk Planning:

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Requirement changes | Medium | High | Scope freeze after approval |
| R2 | Team member unavailability | Low | Medium | Backup planning & task sharing |
| R3 | Schedule delays | Medium | High | Weekly tracking + buffer time |
| R4 | Technical issues | Low | High | Early prototype & testing |
| R5 | System downtime | Low | Medium | Backup system & monitoring |

# 8. Monitoring & Control Planning:

- Monitoring Frequency: Weekly

- Performance Indicators:

  - Task completion %

  - Budget usage

  - Bugs found vs fixed

- Reporting:

  - Weekly reports

  - Google Sheets dashboard

  - Meetings with client

# 9. Communication & Meeting Planning:

### Communication Methods:

- WhatsApp(daily updates)

- Email (formal communication)

- Google Meet(meetings)

| Meeting Type | Frequency | Participants | Agenda |
| --- | --- | --- | --- |
| Team Meeting | Weekly | Atia, Ahmad, Zain | Progress & issues |
| Client Meeting | Bi-weekly | Ahmad + Client | Feedback |
| Sprint Review | Every 2 weeks | Team | Task updates |

# 10. Change Management Planning:

### Process:

- A change request is submitted by the stakeholder.

- Ahmad (Project Manager) analyzes the impact on scope, schedule, and cost.

- The change is reviewed and approved by the client.

- The system and project documents are updated accordingly.

### Approval Authority:

- Minor changes: Approved by Ahmad (Project Manager)

- Major changes: Approved by the Client

11. RACI Matrix:

| Task | R (Responsible) | A (Accountable) | C (Consulted) |
| --- | --- | --- | --- |
| Requirement Gathering | Atia | Ahmad | Client |
| System Design | Zain | Ahmad | Atia |
| Database Design | Zain | Ahmad | - |
| Frontend Development | Zain | Ahmad | - |
| Backend Development | Zain | Ahmad | - |
| Testing | Zain | Ahmad | Client |
| Deployment | Ahmad + Zain | Ahmad | Client |
| Documentation | Atia | Ahmad | Team |

# 12. Rollout Planning:

### Deployment Strategy:

- The system will first be deployed to admin/staff in a beta phase, followed by a full system launch.

### Production Environment:

- The system will be deployed on cloud platforms (AWS / Vercel) with proper backup and security mechanisms.

### Training Plan:

- A 2-hour training session will be conducted for the store owner and admin staff.

- Video tutorials will also be provided for continuous learning and support.

Acceptance Criteria:

- The system is fully functional.

- Critical bugs are fewer than 5.

- Client approval is obtained after User Acceptance Testing (UAT).

- At least 90% positive feedback is received from test users.