NAME:

Ahmad Raza (53302)

Atia Rahat (57325)
                                  Zain Zaheer(53812)

PROGRAM:

BSSE-6

COURSE:

SPM

PROJECT:

Sales Point

DOCUMENT:

Lab 8

SUBMITTED TO:

Sir Waqar Mehmood

# Introduction

A Network Diagram is a graphical representation of project activities and their dependencies. It helps project managers visualize the sequence of tasks required to complete a project.

The Critical Path Method (CPM) is a scheduling technique used to identify the longest path of dependent activities in a project. Activities on the critical path have zero slack, meaning any delay in these tasks will directly delay the entire project.

Network diagrams are widely used in software project management for planning, scheduling, monitoring, and controlling project activities.

# Key Concepts

## 2.1  Activity

An activity is a task that consumes time and resources. Examples include:

- Requirement Gathering

- System Design

- Coding

- Testing

## 2.2  Dependency

A dependency defines the relationship between activities. Types of dependencies:

- Finish to Start (FS) — most common; successor starts only after predecessor finishes.

- Start to Start (SS) — successor can start as soon as predecessor starts.

- Finish to Finish (FF) — successor can finish only after predecessor finishes.

- Start to Finish (SF) — rarely used; successor cannot finish until predecessor starts.

## 2.3  Critical Path

The longest sequence of dependent activities in a project is called the Critical Path. Key points:

- Activities on the critical path have zero slack.

- Delay in critical activities delays the entire project.

- Critical path determines the minimum project completion time.

## 2.4  Slack / Float

Slack  =  LST − EST

Slack  =  LFT − EFT

## 2.5  Forward Pass Formulae

Used to calculate Earliest Start Time (EST) and Earliest Finish Time (EFT):

EST(first activity)  =  0

EST  =  maximum EFT of all predecessors

EFT  =  EST + Duration

## 2.6  Backward Pass Formulae

Used to calculate Latest Finish Time (LFT) and Latest Start Time (LST):

LFT(last activity)  =  EFT(last activity)

LFT  =  minimum LST of all successors

LST  =  LFT − Duration

# Software / Tools Required

- Microsoft Project / Draw.io / Lucidchart / Visio

- Calculator

- Notebook and Pen / Pencil

# Scenario — Online Learning Management System (LMS)

A software house is developing an Online Learning Management System (LMS). The project manager wants to create a network diagram and identify the critical path to ensure timely project completion. The following activities have been identified:

| Act. | Description | Duration (Days) | Predecessor(s) | Path | Notes |
| --- | --- | --- | --- | --- | --- |
| A | Requirement Gathering | 3 | — | Critical | — |
| B | Feasibility Study | 2 | A | Critical | — |
| C | System Design | 4 | B | Critical | — |
| D | Database Design | 3 | B | Non-Critical | Slack = 2 |
| E | Coding Module 1 | 5 | C | Critical | — |
| F | Coding Module 2 | 4 | D | Non-Critical | Slack = 2 |
| G | Integration | 2 | E, F | Critical | — |
| H | Testing | 3 | G | Critical | — |
| I | Deployment | 1 | H | Critical | — |

# Procedure

## Step 1 — Identify Activities

List all project activities with their durations and dependencies (see the activity table above).

## Step 2 — Draw Network Diagram (AON)

Create nodes (boxes) for each activity and connect them with arrows according to dependencies. The AON (Activity-On-Node) format uses the following node structure:

| AON Node Structure |  |  |  |
| --- | --- | --- | --- |
| EST | Duration | EFT | (diagram cell) |
| Activity ID |  |  |  |
| LST | Slack | LFT | (diagram cell) |

Basic network flow for the LMS project:

A → B → C → E → G → H → I  (main critical path)

B → D → F → G               (parallel non-critical branch)

## Step 3 — Forward Pass

Calculate EST and EFT for every activity by traversing the network from left to right (start to finish). Where multiple predecessors exist, take the maximum EFT.

## Step 4 — Backward Pass

Calculate LFT and LST by traversing the network from right to left. Set LFT of the last activity equal to its EFT. Where multiple successors exist, take the minimum LST.

## Step 5 — Calculate Slack

Compute slack for each activity. Activities with slack = 0 form the critical path.

# Solution Table — LMS Project

The table below shows the complete CPM analysis. Highlighted rows (amber) indicate critical path activities with zero slack.

| Act. | Description | Dur. | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirement Gathering | 3 | 0 | 3 | 0 | 3 | 0 |
| B | Feasibility Study | 2 | 3 | 5 | 3 | 5 | 0 |
| C | System Design | 4 | 5 | 9 | 5 | 9 | 0 |
| D | Database Design | 3 | 5 | 8 | 7 | 10 | 2 |
| E | Coding Module 1 | 5 | 9 | 14 | 9 | 14 | 0 |
| F | Coding Module 2 | 4 | 8 | 12 | 10 | 14 | 2 |
| G | Integration | 2 | 14 | 16 | 14 | 16 | 0 |
| H | Testing | 3 | 16 | 19 | 16 | 19 | 0 |
| I | Deployment | 1 | 19 | 20 | 19 | 20 | 0 |

Critical Path: A → B → C → E → G → H → I Total Project Duration: 20 Days Non-Critical Activities: D (slack: 2), F (slack: 2)

# Critical Path Identification — LMS

Activities with zero slack (Slack = 0):

A → B → C → E → G → H → I

These activities form the critical path. Any delay in any one of them will directly extend the project completion date.

| Item | Analysis |
| --- | --- |
| Activities D and F | 2 days slack each — can be delayed up to 2 days without impacting delivery. |
| Total duration | 20 days minimum (determined by the critical path length). |
| Merge point at G | Both branches (C→E and D→F) converge at G. G's EST is determined by the longer path (E finishes on day 14). |

# Expected Output

Students should submit:

- A complete network diagram drawn using AON format.

- Calculated EST, EFT, LST, and LFT for each activity.

- Computed slack values for all activities.

- Identification of the critical path.

- Determination of total project completion time.

# Result

The Network Diagram for the LMS project was successfully created. Using CPM analysis, the critical path was identified as:

A → B → C → E → G → H → I

The minimum project completion time is 20 days.

- Practice Task — Scenario 1: Mobile Banking Application

A software company is developing a Mobile Banking Application. The project manager wants to analyze project activities using CPM.

| Act. | Description | Duration | Predecessor(s) | Path | Notes |
| --- | --- | --- | --- | --- | --- |
| A | Initial Planning | 2 | — | Critical | Slack = 0 |
| B | UI/UX Design | 4 | A | Critical | Slack = 0 |
| C | Database Design | 3 | A | Non-Critical | Slack = 4 |
| D | Backend Development | 5 | B | Critical | Slack = 0 |
| E | Frontend Development | 2 | C | Non-Critical | Slack = 4 |
| F | Integration & Testing | 4 | D, E | Critical | Slack = 0 |
| G | Final Testing & QA | 3 | F | Critical | Slack = 0 |

## CPM Calculations — Banking App

| Act. | Description | Dur. | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Initial Planning | 2 | 0 | 2 | 0 | 2 | 0 |
| B | UI/UX Design | 4 | 2 | 6 | 2 | 6 | 0 |
| C | Database Design | 3 | 2 | 5 | 6 | 9 | 4 |
| D | Backend Development | 5 | 6 | 11 | 6 | 11 | 0 |
| E | Frontend Development | 2 | 5 | 7 | 9 | 11 | 4 |
| F | Integration & Testing | 4 | 11 | 15 | 11 | 15 | 0 |
| G | Final Testing & QA | 3 | 15 | 18 | 15 | 18 | 0 |

Critical Path: A → B → D → F → G Total Project Duration: 18 Days Non-Critical Activities: C (slack: 4), E (slack: 4)

## Analysis Notes

Path A → B → D → F → G is the critical path. Path A → C → E → F → G is non-critical:

- Activity C has slack of 4 days — can start up to 4 days late without delaying the project.

- Activity E has slack of 6 days — considerable float available.

- F and G are critical because both paths converge at F; F's EST is determined by D (finishes day 11).

- Practice Task — Scenario 2: E-Commerce Website Development

A software house is building an E-Commerce Website for online shopping. The project manager wants to determine the critical path to complete the project efficiently.

| Act. | Description | Duration | Predecessor(s) | Path | Notes |
| --- | --- | --- | --- | --- | --- |
| A | Requirement Analysis | 3 | — | Critical | Slack = 0 |
| B | UI/UX Design | 4 | A | Critical | Slack = 0 |
| C | Database Setup | 2 | A | Non-Critical | Slack = 1 |
| D | Frontend Development | 5 | B | Critical | Slack = 0 |
| E | Backend Development | 6 | C | Non-Critical | Slack = 1 |
| F | API Integration | 3 | D, E | Critical | Slack = 0 |
| G | Testing | 4 | F | Critical | Slack = 0 |
| H | Deployment | 2 | G | Critical | Slack = 0 |

## Forward Pass — E-Commerce

Calculating EST and EFT from left to right:

| Act. | EST | Duration | EFT | Predecessor EFTs | Calculation |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 3 | 3 | None | EST=0, EFT=0+3=3 |
| B | 3 | 4 | 7 | A=3 | EST=max(3)=3, EFT=3+4=7 |
| C | 3 | 2 | 5 | A=3 | EST=max(3)=3, EFT=3+2=5 |
| D | 7 | 5 | 12 | B=7 | EST=max(7)=7, EFT=7+5=12 |
| E | 5 | 6 | 11 | C=5 | EST=max(5)=5, EFT=5+6=11 |
| F | 12 | 3 | 15 | D=12, E=11 | EST=max(12,11)=12, EFT=12+3=15 |
| G | 15 | 4 | 19 | F=15 | EST=max(15)=15, EFT=15+4=19 |
| H | 19 | 2 | 21 | G=19 | EST=max(19)=19, EFT=19+2=21 |

## Backward Pass — E-Commerce

Calculating LFT and LST from right to left (project duration = 21 days):

| Act. | LFT | Duration | LST | Successor LSTs | Calculation |
| --- | --- | --- | --- | --- | --- |
| H | 21 | 2 | 19 | End | LFT=21, LST=21-2=19 |
| G | 19 | 4 | 15 | H=19 | LFT=min(19)=19, LST=19-4=15 |
| F | 15 | 3 | 12 | G=15 | LFT=min(15)=15, LST=15-3=12 |
| E | 12 | 6 | 6 | F=12 | LFT=min(12)=12, LST=12-6=6 |
| D | 12 | 5 | 7 | F=12 | LFT=min(12)=12, LST=12-5=7 |
| C | 6 | 2 | 4 | E=6 | LFT=min(6)=6, LST=6-2=4 |
| B | 7 | 4 | 3 | D=7 | LFT=min(7)=7, LST=7-4=3 |
| A | 3 | 3 | 0 | B=3, C=4 | LFT=min(3,4)=3, LST=3-3=0 |

## Complete CPM Solution Table — E-Commerce

| Act. | Description | Dur. | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirement Analysis | 3 | 0 | 3 | 0 | 3 | 0 |
| B | UI/UX Design | 4 | 3 | 7 | 3 | 7 | 0 |
| C | Database Setup | 2 | 3 | 5 | 4 | 6 | 1 |
| D | Frontend Development | 5 | 7 | 12 | 7 | 12 | 0 |
| E | Backend Development | 6 | 5 | 11 | 6 | 12 | 1 |
| F | API Integration | 3 | 12 | 15 | 12 | 15 | 0 |
| G | Testing | 4 | 15 | 19 | 15 | 19 | 0 |
| H | Deployment | 2 | 19 | 21 | 19 | 21 | 0 |

Critical Path: A → B → D → F → G → H Total Project Duration: 21 Days Non-Critical Activities: C (slack: 1), E (slack: 1)

## Analysis Notes

The critical path A → C → E → F → G → H runs through the backend development branch:

- Backend development (E, 6 days) is the longest single activity and drives the schedule.

- B and D are non-critical — UI/UX and frontend development have 4 days of slack each, because the backend takes longer than the frontend.

- F, G, and H are critical because they follow the merge point where both branches converge.

- Conclusion

Network Diagrams and CPM are essential techniques in Software Project Management. They help project managers organize activities, identify dependencies, optimize schedules, and monitor project progress efficiently.

Understanding the critical path ensures better resource allocation and timely completion of software projects. Key takeaways from this lab:

- The critical path is the longest path through the network and equals the minimum project duration.

- Activities on the critical path have zero slack — any delay directly delays the project.

- Non-critical activities have slack, providing scheduling flexibility.

- The forward pass computes EST and EFT; the backward pass computes LST and LFT.

- Slack = LST − EST = LFT − EFT for every activity.

- CPM is most effective when activity durations are known with reasonable certainty.

| LMS Project Critical Path A→B→C→E→G→H→I 20 Days | Banking App Critical Path A→B→D→F→G 18 Days | E-Commerce Site Critical Path A→C→E→F→G→H 21 Days |
| --- | --- | --- |